## 1
6 WEEK CONSTRUCTION PLAN
Project Name | Oldbury Waste | Date |  | 2013-04-15 | Logistics (enter Y/N)
Project No. | C00062 | Project Review No. |  |  | Dwgs | Materials | Access | Plant | Targets | Labour
Section | IES Building | Programme
|  | Programme Ref. |  |  | Check List
[5 empty] | N | N | Y | Y | N | Y
Programme Details |  |  |  |  | Planned Labour Histogram
ID | Area | Comment | Start | Complete | 1 | 2 | 3 | 4 | 5 | 6
[5 empty] | 15.04.13 | 22.04.13 | 29.04.13 | 06.05.13 | 13.05.13 | 20.05.13
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6
33 | High Level Containment | Awaiting steel work and position of attenuators |  |  |  | 1
34 | External Lighting to building |  |  |  | 2
34 | External Lighting Columns | [6 empty] | 2 | 2 | 1
35
37 | Fire alarm Cross site
38 | Access control containment and wiring |  |  |  |  | 1 | 1
38 | Access control
44 | BMS Containment and cable Installation
44
46 | Electrical dead testing |  |  |  | 2
47 | Install MCCB panels and Transformers to MCC rooms
47 | Sub-Main cabling | [5 empty] | 2
| Testing sub-main cables | [6 empty] | 1
47 | Main Bonding/ Earth Bars | Drawing required |  |  |  |  | 1
48
52 | Containment to workshop | Rev DWG required /Scaffold removed |  |  |  | 1
53 | Wiring & final fix lighting & power to workshop | After high level duct
52
54
58
59 | BMS wiring
62 | Lighting & Power final fix to offices | Lights shortfall to be addressed |  |  |  |  | 1
62 | Dead testing Offices
63 |  | 0
64 | Data Cross site wiring | 0
66 | AC wiring to condensers office/workshop area | [6 empty] | 1
71 | MCC1-4&6 Ladder to Tx's |  |  |  |  | 1
74
71 | Fire alarm to MCC rooms
73
73 | MCC6 mount & Terminate Distribution Board |  |  |  | 1
73 | MCC1-6 Condenser containment & wiring | [5 empty] | 1 | 2 |  | 1
73
73 | MCC5 Containment to compressors | Info Required | [6 empty] | 1
73
77 | MCC1 to 4 & 6 Lighting and power final fix | Walls to complete |  |  | 1
77 | MCC5 Wiring & 2nd fix |  |  |  |  | 2
78 | Fire alarm final fix | 0
| Labelling and final snagging IES building | 0 | [7 empty] | 1
| HV Cabling | 0
HV Terminations
| MCC pods wiring/containment | 0 | [6 empty] | 1
| Total target hours | 0 |  |  | 6 | 6 | 6 | 6 | 4 | 3
Note on F12: EMCOR Staff: Enter week number
Note on G12: EMCOR Staff: Enter week number
Note on H12: EMCOR Staff: Enter week number
Note on I12: EMCOR Staff: Enter week number
Note on J12: EMCOR Staff: Enter week number
Note on K12: EMCOR Staff: Enter week number

## 2
6 WEEK CONSTRUCTION PLAN
Project Name | Oldbury Waste | Date |  | 2013-04-15 | Logistics (enter Y/N)
Project No. | C00062 | Project Review No. |  |  | Dwgs | Materials | Access | Plant | Targets | Labour
Section | EMR | Programme
|  | Programme Ref. |  |  | Check List
[5 empty] | Y | Y | Y | Y |  | N
Programme Details |  |  |  |  | Planned Labour Histogram
ID | Area | Comments | Start | Complete | 1 | 2 | 3 | 4 | 5 | 6
[5 empty] | 15.04.13 | 22.04.13 | 29.04.13 | 06.05.13 | 13.05.13 | 20.05.13
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6
| Containment between Grid Lines D & C GL 13-15 |  |  |  | 1
| Containment between Grid Lines D & C GL 1 |  |  |  |  | 1
vesda pipe work Grid Lines D & C
Busbar Between Grid Lines D & C
Light fittings Grid Lines D & C
| Electrical Secondary Containment | [5 empty] | 1
| Containment between Grid Lines C & B GL 12 |  |  |  | 1
| Containment between Grid Lines C & B GL 1 | [5 empty] | 1
Vesda pipe work between Grid Lines C & B
| Busbar between Grid Lines C & B |  |  |  | 1 | 0.5
| Light fiffings between Grid Lines C & B |  |  |  | 1 | 0.5
| Electrical Secondary Containment | [5 empty] | 1
0
| Containment between Grid Lines B & A GL12 + |  |  |  |  | 0.5
| Containment between Grid Lines 1 &12 | [5 empty] | 1
| Containment between Grid Lines B & A Grid Line 1 | [6 empty] | 1
Vesda pipe work between Grid Lines B & A
| Busbar between Grid Lines B & A & A to Aa |  |  |  |  | 1
| Light fiffings between Grid Lines B & A & A to Aa | 0 |  |  |  | 0.5
| Electrical Secondary Containment | [6 empty] | 1
| Remove containment between Grid Lines E & D | [6 empty] | 1
| Containment between Grid Lines E & D Grid Line 12 | [6 empty] | 1
| Containment between Grid Lines E & D Grid Line 6 | [6 empty] | 2
| Containment between Grid Lines E & D Grid Line1 | 0 | [5 empty] | 1
| Vesda pipe work between Grid Lines E & D | 0
| Busbar between Grid Lines E & D | 0 | [6 empty] | 0.5
| Light fiffings between Grid Lines E & D | 0 | [6 empty] | 0.5
| Electrical Secondary Containment | 0 | [6 empty] | 1
| 0 | 0
| Containment drops to Low level | 0 |  |  |  |  | 2
| 0 | 0
0
| Offices containment | 0 |  |  | 2 | 2 | 2
| Offices wiring small power and Lighting | 0 | [5 empty] | 2 | 2
FA wiring to offices
| Data wiring to Offices | 0
| Sub-Main Wiring | 0 | [7 empty] | 8
| General Wiring to EMR Building | 0 | [6 empty] | 4 | 4
| Building mouted external lighting | 0 | [7 empty] | 2
| Mount Distribution Boards | 0 | [6 empty] | 1
FA wiring To EMR Building
TX1 Compound
TX2 & 3 Compound
| TX4 Compound | 0
| 0 | 0 |  |  | 6 | 6 | 8 | 9 | 9 | 14
Total target hours